## Readiness Tracker
Workstream | Owner | Status | Current Note | Risk Level | Dependency | Next Action
Product concept | Marketing Lead | Complete | Review message consistency | Medium | Consumer insight summary | Confirm final wording for leadership brief
Packaging artwork | Design Lead | At risk | Pending final claim review | High | Legal review | Confirm approved claim wording
Supply readiness | Supply Planner | On track | Validate initial stock allocation | Medium | Forecast lock | Check allocation by channel
Sales enablement deck | Sales Capability Lead | Blocked | Needs final product claims | High | Packaging artwork | Update deck after claim approval
E-commerce content | Digital Commerce Lead | At risk | Images pending | Medium | Packaging artwork | Confirm image availability
Customer FAQ | Customer Care Lead | On track | Draft ready for review | Low | Issue response guideline | Review top questions
Finance margin check | Finance Partner | Complete | Scenario reviewed | Low | Promotion assumptions | Share sensitivity note
Training schedule | HR Partner | On track | Workshop slot reserved | Low | Sales enablement deck | Confirm attendees
Channel launch checklist | Channel Lead | At risk | Some owner fields incomplete | Medium | Sales enablement deck | Assign missing owners
Leadership update | Marketing Lead | Blocked | Waiting for risk summary | High | All workstreams | Prepare concise decision slide

## Read Me
Purpose | Fictional launch readiness tracker for Microsoft 365 Copilot workshop practice.
Important limitation | Data does not include real brand names, launch dates, budgets, retailers, or final commercial targets.
Suggested checks | Count workstreams by Status and identify High risk or Blocked items.